## Config (hidden)
Status | Team Members | Technical State | Priority
Done | Oussama | UI Only | Critcal
Ready for Review | Amr | Backend Connected | High
In Progress | Khodor | Logic Related | Normal
Buggy (Needs Fix) |  | Other
Not Started

## Progress Review
Category | Feature/Module | Assigned To | Technical State | Status | Priority | Feedback & Pending Comments | Dev Notes | Last Updated | Deadline
Authentication | Login |  | Backend Connected | Ready for Review | High | Everytime the user login, it shows to complete profile
Autentication | Login |  | Backend Connected | Ready for Review | High | If user signup using Gmail service, then signed up using add email and used the same Gmail. It creates double account for the same email
Event Creation | User Profile |  | Logic Related | Ready for Review | Normal | User can create an Event even if no profile created, so better to remove the skip for now from the view where the user needs to fill the name, phone .. And its ok to skip for now in the next screen where the user will be filling business information unless it will be linked anywhere inside event creation
Event Creation | Waitlist capacity |  | logic Related | Ready for Review | Normal | Waitlist capacity cant be more than the max. attendees, and the field can take any value where it should be only numerical
Event Creation | Max Attendees |  | logic Related | Ready for Review | Normal | this field should be Numerical only
Authentication | Email Varification |  | Backend Connected | Not Started | Normal | Verification emails should be sent from Eventra not from Supabase Auth
Event Creation | Speakers |  | Logic Related | Ready for Review | Normal | Adding the experience tags as a list so user can choose from
Event Creation | Speakers |  | backend Connected | Ready for Review | Normal | when user clicks to edit the speaker details, the name of the speaker is not shown and the field is empty, speaker's name that was there before the edit should show
Event Creation | Schedule |  | logic Related | Ready for Review | Normal | Max Capacity should not be more than the max. attendees and the field takes any value where it should be only numerical
Event Creation | Schedule |  | logic Related | Ready for Review | high | User can schedule two sessions or workshops in the same venue at the same date and time, where this should not happen. And an attention notification should popup to let the user know that this slot (time) is already scheduled
Event Creation | Schedule |  | Logic Related | Ready for Review | High | User can schedule two sessions or workshops in the same venue at the same date and time, where this should not happen. And an attention notification should popup to let the user know that this slot (time) is already scheduled
Registration | Ticketing |  | Logic Related | Not Started | High | Payment gateway is missing; paid tickets currently register users for free without charging
Logistics | Calculators |  | Logic Related | In Progress | Normal | Freight and Load calculators are not returning results because the API base URL is unconfigured
Access Control | RBAC |  | Logic Related | In Progress | High | Row Level Security (RLS) in Supabase is too open; users can potentially see or edit data they don't own
Admin | Reporting |  | Logic Related | Not Started | Normal | Global reporting and cross-event analytics are currently placeholders or mock data
Event Creation | Design Studio |  | Logic Related | In Progress | Normal | The website preview in the Design Studio is only desktop-optimized; users can't see how the event page looks on mobile
Community | Networking |  | Logic Related | Not Started | Normal | Meeting notifications are sent but there is no 'Accept/Decline' flow for recipients yet

## Design Studio
Settings that Design Studio Sections should include
Hero Section
1- Add logo Switch
2- Change title (Text Field)
3- Change tagline or description (Text field)
4- Sign up button (Switch hide or show)
5- Sign up button text change
6- Additional button (switch (hide or show)
7- Additional button (Text change)
8- Cover photo
9- cover video (PAID)
10- shadow opacity
11- Block name
12 - Class Name
13- CSS (PAID) (text area to add CSS )
About Section
1- WYSIWYG Editor ( User can add the title and text and format it as he wants )
2- Style ( Text only, Image left, Image Right, Image top)
3- Add image field
4- Add button ( Switch ) + field to edit the button label
5- spacing ( default, compact, medium, custom)
6- Block name
7- Class name
8- CSS text Area ( PAID)
Gallery
1- upload up to 6 images
2- drop, add feature ( prefered size 4:3)
3- Grid layout ( like 2x2, 3x3 )
4- Spacing ( Compact, Medium, spacious, custom (PAID)
5- Block name
6- Class Name
7- CSS Text Area (PAID)
Location
1- Textarea ( better to be placeholder and it can filled directly with venue field when event created
2- Map ( switch show or hide)
3- CTA button ( switch show or hide ) + field to add label in case show
Other sections we can just add simple features, like show or hide for items ( like for speakers we can have a switch to hide speaker image, or style of grid how the speakers are shown as PAID feature), we. Can go deeper in this according to effort needed and time constraints

## Dynamic KPIs Dev Roadmap
Phase | Component | Action | Example Data (Dummy JSON) | Description
1. Blueprint | event_templates (Table) | Create Once | type: "Webinar" config: [ {"key": "view_time", "ui": "Circular", "label": "Avg Watch", "color": "primary"} ] | Define the KPIs and their default configuration for each event type. Uses variable names for colors (e.g., primary) to stay brand-consistent.
2. Creation | kpi_config (Column) | Triggered Copy | [ {"key": "view_time", "ui": "Circular", "label": "Avg Watch", "color": "primary"} ] | Add data for the KPIs from the template on event creation. The Frontend reads this to decide what to draw.
3. Logic | kpi_values (Column) | SQL Engine Update | { "view_time": 45.8, "last_updated": "2026-01-15" } | KPIs' Values where SQL function calculates the number and saves it here.
4. Visual | Frontend Component | Dynamic Render | <CircularProgress value={values.view_time} color="var(--primary)" /> | Maps the ui type to a component and the color variable to a CSS theme variable.

## Events KPIs
PLEASE NOTE THAT THIS IS JUST AN IDEA AND RESEARCH, SO WE CAN DISCUSS AND SEE WHATS RELEVANT AND HOW TO SOLVE IT TOGETHER
Event Category | KPI Label | Component | Description | Data Calculation Logic
COMMON (Global) | Reg. Velocity | Line Chart | Monitors signup speed to optimize marketing and ad spend. | COUNT(registrations) grouped by day
COMMON (Global) | Check-in Rate | Progress Bar | Measures actual attendance vs. registrations to see "no-show" rates. | (Checked_in / Total Registered) * 100
COMMON (Global) | Engagement | Circular % | Tracks active participation; shows if the platform is being used. | % of users with 1+ interaction log
COMMON (Global) | Net Revenue | Stat Card | Clear view of the bottom line after all transaction fees. | SUM(ticket_price) - SUM(fees)
--- | --- | --- | --- | ---
Conference | Networking Density | Stat Card | Proves value by showing how many new connections were made. | Total Connections / Total Attendees
| Session Pop. | Top List | Identifies "Superstar" speakers to plan for future events. | Top 5 Sessions by "Add to Schedule"
| Sponsor ROI | Stat Card | Provides hard data to sponsors on total leads generated. | SUM(exhibitor_badge_scans)
| Content Reach | Stat Card | Measures how many users actually "took home" your resources. | COUNT(unique_document_downloads)
Workshop | Completion Rate | Progress Bar | Ensures learning goals were met; identifies if content is too long. | (Completed_Users / Total) * 100
| Mentor Time | Stat Card | Tracks the value of direct access to instructors/experts. | Total Breakout Minutes / Total Attendees
| Skill Gain | Comparison | Proves the tangible "Before vs. After" value of the session. | Avg(Post_Test) - Avg(Pre_Test)
| Material Utility | Circular % | Shows if workbooks/tools were helpful or ignored. | (Unique Workbook opens / Total) * 100
Webinar | Attention Ratio | Circular % | Pinpoints exactly when the audience lost interest or left. | (Avg_Watch_Time / Duration) * 100
| Interaction Rate | Stat Card | Measures engagement through polls and live Q&A activity. | (Polls + Questions) / Live Viewers
| Conversion Vel. | Stat Card | Measures how fast users acted on your "Offer" or CTA. | Avg(CTA_Click_Time - CTA_Show_Time)
| Audience Health | Area Chart | Shows real-time viewership peaks and valleys. | Concurrent Viewers per Minute
Networking | Match Success | Progress Bar | Measures if users actually found someone to talk to. | (Users with 1+ Meeting / Total) * 100
| Conversation Depth | Stat Card | Distinguishes between "hi" and real business discussions. | Total Messages / Total Connections
| Interest Match | Pie Chart | Shows if the "right" people are connecting with each other. | % Connections sharing Industry Tags
| Follow-up Rate | Stat Card | Tracks intent to continue the relationship outside the app. | COUNT(LinkedIn_Link_Clicks)
Trade Show | Exhibitor Perf. | Stat Card | Identifies which booths were the most successful and active. | Total Scans / Number of Exhibitors
| Floor Heatmap | Ranking | Shows which areas of the floor had the most "dwell time." | Top 10 Booths by Minutes Stayed
| Lead Quality | Pie Chart | Helps organizers verify if attendees were high-value buyers. | % of scans tagged "Hot Lead"
| Inquiry Volume | Stat Card | Measures direct "Sales Interest" via Quote Requests. | COUNT(Clicks on "Request Quote")
Summit | Exec Participation | Stat Card | Proves the "High-Level" nature of the event by tracking VIPs. | Active VIPs / Total VIPs
| VIP Retention | Circular % | Tracks if the "Exclusive" content kept VIPs engaged. | Avg minutes in VIP Lounge vs General
| Sentiment Score | Stat Card | Real-time "mood meter" based on reactions (likes/claps). | Positive Reactions / Total Reactions
| Strategic Reach | Stat Card | Tracks the viral spread of key Summit reports/papers. | COUNT(Whitepaper/Report Shares)
Masterclass | Instructor Access | Stat Card | Highlights the "VIP access" to the master teacher. | COUNT(Resolved Questions by Instructor)
| Replay Rate | Progress Bar | Shows the long-term value of the content after it's live. | (Unique Replay Views / Total) * 100
| Project Subs | Progress Bar | Measures student commitment to applying what they learned. | (Final Uploads / Total Enrolled) * 100
| Referral Score | Stat Card | Tracks how many students invited others to the class. | COUNT(Referral Link Clicks)
Training | Compliance | Progress Bar | Critical for legal safety; ensures all rules were seen. | % view of Mandatory Slides
| First-Try Pass | Circular % | Measures how effective the training was the first time. | Users(Pass on Try 1) / Total Users
| Time-to-Certify | Stat Card | Measures efficiency; how fast do users finish the course? | Avg(Cert_Time - Start_Time)
| Knowledge Gap | Ranking | Pinpoints exactly which topic needs more explanation. | Question ID with most Incorrects
Bootcamp | Intensity Index | Stat Card | High activity per day predicts higher graduation rates. | Avg Active Hours per Student per Day
| Peer-to-Peer Help | Stat Card | Tracks community strength; students helping students. | COUNT(Forum Replies) / Total Students
| Milestone Vel. | Progress Bar | Early warning system for students falling behind schedule. | Avg Time to Finish Phase 1 vs Goal
| Project Ready | Pie Chart | Shows how many students are prepared for the final. | % Students with "Approved" Topics
Hackathon | Submission Ratio | Progress Bar | The final "Productivity" score; ideas turned into code. | (Submissions / Total Teams) * 100
| Code Activity | Stat Card | Proves technical effort through real developer commits. | SUM(Git Commits via Webhook)
| Team Diversity | Stat Card | Measures "Innovation" by tracking cross-skill teams. | Avg Unique Skill Tags per Team
| Judging Progress | Progress Bar | Ensures fairness; tracks if all projects are being scored. | % Projects with 3+ Judge Scores
Award Ceremony | Voting Turnout | Circular % | Measures community "Hype" and support for nominees. | (Unique Voters / Total Reg) * 100
| Category Heat | Pie Chart | Identifies which categories were the most popular. | Total Votes per Category
| Social Amp | Stat Card | Measures free marketing via "Winner" social shares. | COUNT(Winner Asset Downloads)
| Live Peak | Stat Card | The "Super Bowl" moment; highest viewership during reveal. | Max(Viewers) during Winner Segment
Other | Goal Progress | Progress Bar | Allows organizers to track a custom target they set. | Current Value / User Defined Goal
| Total Interaction | Stat Card | A "catch-all" for general platform activity. | SUM(All Button Clicks & Chats)
| Survey Rate | Progress Bar | Measures feedback quality; how many gave an opinion. | (Surveys / Total Attendees) * 100
| Return Rate | Stat Card | Tracks "Loyalty"; how many repeat customers are here. | Attendees with 1+ Past Event History